F. 6-17/2010-KVS/HQ(WK-I)/	                                                         28 .03.2013

The Deputy Commissioner

Kendriya Vidyalaya Sangathan

All Regional Offices

Sub:	Proposals for construction of additional accommodation & additional staff quarters at KVs under your region.

Sir/Madam,

You are aware that, in the past KVS Works Branch had sanctioned estimates received from Regional Offices in respect of above cited works.  However during the past two years no new proposals could be sanctioned due to paucity of funds.

02.	During execution of some of the sanctioned works, we have come across certain problems at belated stage of construction, which led to delay/cancellation of works.  These are:-

(i)	Proposals/estimate received from the school/through Regional Office without the approval of Chairman, VMC, DEO etc. and objections is raised by sponsors subsequently.

(ii)	Submission of incomplete estimate without making provision/ incorporation of essential services i.e. water supply/electrification/sewage disposal/system strengthening i.e. enhancement of load/installation of transformer and any other mandatory requirements imposed by the local body.

(iii)	 Existence of HT/LT electric lines, trees, old structures encroachment etc on the proposed piece of land.

(iv)       Estimate submitted without ensuring completion of land lease formalities             infavour of KVS and

(v)        Clauses included in the lease about construction of additional/new works.

03.	  The new proposals relating to additional accommodation & additional staff quarters are likely to be sanctioned  in the forthcoming financial year (2013-14) as the fund position improves and  to streamline the submission of proposal/estimates by Regional Office, new formats have been devised for circulation to all Principals (set enclosed).

04.	 Accordingly, it is requested that all new proposals must be submitted in these formats alongwith estimates with your specific recommendations.  Concerted and sincere efforts should be made to get estimates from CPWD/MES federal construction agencies of Govt. of India, failing which estimates can be obtained from any other empanelled agency of KVS.  It may be noted that proposals not received in the enclosed formats or incomplete proposals will not be considered in KVS (HQ) and no correspondence will be made in this regard.   You are, therefore, hereby directed to go-through all the aspects narrated above before forwarding to proposals.

05. 	Since availability of budget in the F.Y 2013-14 may not be adequate for accommodating all the proposals received from different regional offices, you must identify such Kendriya Vidyalayas and priority list made where construction of additional rooms is absolutely required. Accordingly the proposals alongwith estimates may be forwarded for approval.

06.	Please give your personal attention to these instructions in future.

Yours faithfully,

Encl:As above

-sd-

(G.K. SRIVASTAVA)

Additional Commissioner (Admn)

KENDRIYA VIDYALAYA SANGATHAN

REGIONAL OFFICE

F. No: __________________________                                 Date:

The Additional Commissioner (Admn)

KVS (HQ)

New Delhi

Sub: Proposal for construction of _________________ at KV ___

Sir,

I am enclosing herewith a proposal along with estimate and other documents received from Principal, KV ____________ for construction of __________. The proposal has been examined at Region level and found in order. The proposed work is very much essential in the interest of students/ staff of the Vidyalaya.

02.  Further the Principal, KV had aleady requested CPWD / MES followed by reminders for submission of preliminary drawings alongwith estimate, check list, certificate –I , but so far no response has been received. Hence estimate and aforesaid documents have been obtained from empanelled Govt. agency of KVS.

03.  The proposed work is hereby recommended for issue of AA&ES with sanction of funds.

Encl: a/a

Yours faithfully,-

sd-

Deputy Commissioner

NOTE: - Para no. 02 is not required in case estimate is obtained from CPWD or MES

For Additional Rooms

REQUIREMENT OF BALANCE  ACCOMMODATION FOR UPGRADATION OF EXISTING SCHOOL BUILDING

Name of K V: ________________Region: __________Sponsor:___________

To be upgraded from _____ Type to _____ Type

| S No | Name of Room | Size in Sq. mt. as per norms | Requirement of rooms as per norms | Available no. of rooms | Balance requirement 4 - 5 | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1 | Class Rooms | 7.00 x 7.00 | A - 24 B -36 C - 48 |  |  |  |
| 2 | Computer Labs | 7.00 x 10.60 | A - 2 B / C - 3 |  |  |  |
| 3 | Sc. Labs | 7.00 x 8.80 & 7.00 x 3.60 | A / B /C - 3 |  |  |  |
| 4 | Jr. Sc. Lab | 7.00 x 10.60 | B / C - 1 |  |  |  |
| 5 | S.Sc/Geo/Resource Room (P) | 7.00 x 3.40 | 1 |  |  |  |
| 6 | S.Sc/Geo/Resource Room (H/s) | 7.00 x 7.00 | 1 |  |  |  |
| 7 | Activity Room | 7.00 x 10.60 | 1 |  |  |  |
| 8 | Art Room | 7.00 x 10.60 | 1 |  |  |  |
| 9 | SUPW/ Work Shop | 7.00 x 10.60 |  |  |  |  |
| 10 | Library A – 7.00 x 14.20 B – 7.00 x 17.30 C – 7.00 x 21.4 | See in Col. 2 | 1 |  |  |  |
| 11 | Maths Lab | 7.00 x 7.00 | 1 |  |  |  |
| 12 | Principal Room | 7.00 x 7.00 | 1 |  |  |  |
| 13 | Office | 7.00 x 7.00 | 1 |  |  |  |
| 14 | Staff common Room A – 7.00 x 7.00 B – 7.00 x 8.80 C – 7.00 x 10.60 | See in Col. 2 | 1 |  |  |  |
| 15 | VP Room | 3.40 x 3.40 | B / C - 1 |  |  |  |
| 16 | HM Room | 7.00 x 3.40 | 1 |  |  |  |
| 17 | Exam. Room | 7.00 x 3.40 | 1 |  |  |  |
| 18 | NCC/Scout & Guide Room | 7.00 x 7.00 | 1 |  |  |  |
| 19 | PET Room | 7.00 x 7.00 | 1 |  |  |  |
| 20 | General Store | 7.00 x 7.00 | 1 |  |  |  |
| 21 | Medical Room | 7.00 x 3.40 | 1 |  |  |  |

Notes:

- Types of school building  A – Two sections in each class from I to XII

B - Three             -do-

C – Four               -do-

- Rooms sanctioned, but construction yet to start / rooms under construction / rooms constructed but yet to taken over shall also be included in Col. No: 5 with remarks.

- Size of any existing room is less than norms; remarks with size shall be given against the same. However, variation is marginal remarks shall not be given.

Signature of Principal

09/12 ACR

Checklist for approval of preliminary drawings for construction of

additional accommodation / upgradation  for existing school buildings

Name of KV: __________________________

Additional accm / updradation to _____ type school Building

(Tick)                 - A-I (Single section-plinth area 2640 sqmt) in normal 				       	     	      cases (480 students)

- A    (two section - plinth area 4200 sqmt) in normal

Cases (960 students)

- B    (three section - plinth area 5560 sqmt) in normal

Cases (1440 students)

- C    (four section – plinth area 6660 sqmt) in normal

Cases (1920 students)

Agency: ________________

| S.NO. | Description | To be ensured by Architect | Remarks of Architect |
| --- | --- | --- | --- |
| 1. | No. of rooms conforming to KVS space norms | Conforming to KVS space norms/ Few rooms not conforming to KVS space norms, but are functional ( give reasons in remarks col ) |  |
| 2. | Size of rooms conforming to KVS space norms | Conforming to KVS space norms/ Few rooms not conforming to KVS space norms, but are functional ( give reasons in remarks col ) |  |
| 3. | Plinth area | As per KVS norms /Higher than KVS space norms ( give reasons in remaks col ) |  |
| 4. | Provision of cement concrete black board in class rooms | to be made |  |
| 5. | Provision of glass equivalent writing board in other academic related rooms (except class rooms) | to be made |  |
| 6. | Provision of built-in cup board with shutters upto lintel level and pin up boards in class rooms | to be made |  |
| 7. | Provision of built-in cup board with shutters upto lintel in other rooms. | to be made |  |
| 8. | Brief specifications of the project | As per KVS/CPWD & soil report or as per KVS/MES & soil report (details to be furnished) |  |
| 9. | Detail of fitting/fixtures | As per CPWD/KVS or MES/KVS (details to be furnished) |  |
| 10. | Layout of labs with specifications as per KVS space norms | To be developed as per KVS norms |  |
| 11. | Ramp to all floors for differently abled persons and children | To be provided as per yardsticks |  |
| 12. | Toilet in ground floor for differently abled children | To be provided as per yardsticks |  |
| 13. | Drawings with further expansion of school building to next higher category showing required number of rooms in line plan/additions/modifications in dotted lines | To be developed accordingly |  |
| 14 | Provision of 24 nos (minimum) (for A-I, ‘A’ ‘B’) and 30nos. (minimum) (for ‘C’ type) power points and one extra point for teacher, in each computer room. | To be made |  |
| 15 | Whether filling required | If yes, please show the location with dimensions in Drawings mentioning existing GL, Formation level and depth of filling. . |  |
| 16 | Provision of rain water harvesting, fire fighting and other mandatory requirements/ provisions | To be made. Necessary approvals from concerned authorities to be taken before taking up the work and after completion |  |
| 17 | Layout/Preliminary drawings developed as per local bye-laws and national building code/AAI CRZ/ASI/NDMA regulations etc. | Drawing to be developed as per mandatory bye-laws. Necessary approvals to be taken from concerned authorities before taking up the work and after completion |  |
| 18 | Toilets for boys/girls/staff adequately provided at suitable locations in the building as per standards (Boys 60% girls 40% ratio of total no. of students) | Drawing to be developed with adequate numbers as per standards |  |
| 19 | Segregation of wet areas/toilet blocks from walls of main building to prevent seepage. | To be planned accordingly/not possible (given reasons) |  |
| 20 | Attached toilet to principal room and medical room provided | Drawings to be developed accordingly |  |
| 21 | Cooler spaces (inside building at suitable locations provided | Drawings to be developed accordingly |  |
| 22 | Any other required provisions made as per architectural considerations | To be indicated, if any and incorporated |  |
| 23 | Any other provision made as per by-laws and mandatory requirements | To be indicated if any and incorporated |  |
| 24 | Provision Internal Switch Boards/ M.C.B. etc. at lintel level only. | To be ensured |  |
| 25 | Width of corridors in school building | Min.1800 mm for singly loaded. Min.2100 mm for doubly loaded. |  |
| 26 | Explore possibility of singly loaded corridors. | Possibility to be explored. School building fully singly loaded corridor/partly singly loaded corridors. |  |
| 27 | Proposed plinth level of buildings | Higher than G.L of existing outside road / H.F.L of the place/ at par with Recently Constructed Government Buildings in the vicinity (TO be justified) However minimum plinth height 450 mm from formation level. |  |
| 28 | Requirement of retaining wall/ protective measures | Not required / incorporated in drawings. |  |
| 29 | Provision of exhaust Fans. Wherever necessary and security lights on building corners made. | Provision to be made in detailed drawings. |  |
| 30 | Provision of separated toilets for staff gents/ ladies including one each toilet for differently abled persons | To be made |  |

Note:-

(*) – Local by laws and National Codes are final and are to followed wherever contradictions observed above.

Signature of Architect-					                  Signature of Competent 					         Technical Authority of const. agency

09/2012 ACR

CERTIFICATE – I

(This certificate is invariably be obtained from construction agency and submitted alongwith preliminary estimate)

Sub:	Estimate   for construction   of  _______________________________ at  KV __________________

This is to certify that estimate amounting to Rs. _____________________ submitted by our office for the above cited work is a consolidated estimate covering   the following provisions apart from construction of buildings as per scope including internal services :-

- Development of site i.e. internal roads/paths/retaining wall ( if required ), external water supply viz sump, tanks on building, pumps(submersible/booster), area drainage, external sewer arrangement viz. septic tank, soak pits etc.

- Bulk services (civil & elec.)

- Electric service connection including charges payable to local Elec. Board, if any.

- Drinking water including connection and charges payable to local authorities ( if any) and tube-well ( if required )

- All provisions are made after ascertaining demand

- Other provisions as per norms and site conditions,(  if any )

It is further certified that no demolition of existing structures, removal of electric lines, trees etc. is required.

Being ‘Deposit Work’ necessary co-ordination is being made by this department with local authorities and ensure approval of drawings before and after execution of work.  However, Principal, KV will extend his help in this regard.

It is further certified that on completion, these structures can be put in use with commissioning of all services viz. Drinking water, electricity, sewage disposal etc. without any difficulty.

Signature of competent Technical Authority

of Construction Agency

09/12 ACR SQ

CERTIFICATE – II

(This certificate is invariably be furnished by Principal alongwith estimate )

Sub:  Estimate amounting to Rs. __________ framed by  _____________(Name             of construction agency ) for construction of ___________________________at KV, _________________________.

This is to certify that the above construction work has been planned on the  overall land measuring _______ acres already transferred to this KV on lease / permanent grant basis . Further the piece of land is clear and free from obstructions, encroachments, trees, elec. Lines, litigations, court cases. No demolition of  structures is involved.

The proposal and construction agency have been approved  in VMC meeting held on __________. The location of proposed construction work has been decided by a team of officials of VMC (Chairman or his authorized representative ), Construction agency, and the undersigned.

Signature of Principal

09/12 ACR SQ

CERTIFICATE –III

( To be obtained from competent authority of Sponsors )

GRANT OF APPROVAL FOR CONSTRUCTION

Principal, Kendriya  Vidyalaya ______________approached this office for grant of approval/ permission  to undertake construction of _______________

on the basis of  drawings developed and estimate framed by ______________

on the land measuring ________ acres allotted on  lease / permanent grant to this KV by _____________. As per allotment conditions prior permission / approval is to be obtained from competent authority.

The undersigned has no objection in taking up this work on the aforesaid land and approval / permission is hereby granted in this regard.

SIGNATURE OF COMPETENT AUTHORITY

WITH DATE & SEAL

Note:  For Defence secotor KVs  -  DEO  ( Compulsory ) and  also  Chairman , VMC ( or any other  authorized Officer )

For Railway Sector KVs - DRM and/or, GM  (to be confirmed from sponsors ) ,and also Chairman , VMC ( or any other  authorized officer )

For State Govt. Sector - DM/ Collector ( or any other authorized officer )

For KVs not covered above - may be confirmed from Sponsors.

09 /12 ACR SQ

For Staff Quarters

Checklist for approval of preliminary drawings for construction of

Staff qrarters

Name of KV & State: _________________________

Name of Region: __________________

Sponsoring Authority: ____________________

Name of construction Agency: ________________

| S.NO. |  | Description |  | To be ensured by Architect |  | Remarks of Architect |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  | No. of Staff Quarters proposed by KV category wise |  | Type – I ______ units II _______ units III _______ units IV ______ units V ______ units |  |  |
| 2. |  | Size of rooms and plinth area conforming to CPWD / MES norms and yardsticks. |  | Conforming to _____norms and yardsticks |  |  |
| 3. |  | Plinth area of each unit, Servant Qut., Garage, Cycle sheds, scooter sheds |  |  |  |  |
| 4 |  | Total Plinth area |  | __________ Sq. mt. |  |  |
| 5 |  | Provision of attached servant quarter with main unit of Type- V made as per approved plinth area |  |  |  |  |
| 6 |  | Provision of Cycle shed for T-I and T – II, Scooter shed for T – III and T- IV and Garage for T – V |  |  |  |  |
| 7 | Brief specifications of the project |  | As per CPWD & soil report or as per/MES & soil report (details to be furnished) |  |  |  |
| 8 | Detail of fitting/fixtures |  | As per CPWD or MES (details to be furnished in drawings) |  |  |  |
| 9 | Provision is made for future construction of additional units with average plinth area of T-II, III and IV |  |  |  |  |  |
| 10 | Whether filling required |  | If yes, please show the location with dimensions in Drawings mentioning existing GL, Formation level and depth of filling. . |  |  |  |
| 11 | Provision of rain water harvesting, fire fighting and other mandatory requirements/ provisions |  | To be made. Necessary approvals from concerned authorities to be taken before taking up the work and after completion |  |  |  |
| 12 | Layout/Preliminary drawings developed as per local bye-laws and national building code/AAI CRZ/ASI/NDMA regulations etc. |  | Drawing to be developed as per mandatory bye-laws. Necessary approvals to be taken from concerned authorities before taking up the work and after completion |  |  |  |
| 13 | Provision of open area for get togethers and small functions made ( subject to availability of land ) |  | To be incorporated |  |  |  |
| 14 | Any other required provisions made as per architectural considerations |  | To be indicated, if any and incorporated |  |  |  |
| 15 | Any other provision made as per by-laws and mandatory requirements |  | To be indicated if any and incorporated |  |  |  |
| 16 | Proposed plinth level of buildings |  | Higher than G.L of existing outside road / H.F.L of the place/ at par with Recently Constructed Government Buildings in the vicinity (TO be justified) However minimum plinth height 450 mm from formation level. |  |  |  |
| 17 | Requirement of retaining wall/ protective measures |  | Not required / incorporated in drawings. |  |  |  |

Note:-

(*) – Local by laws and National Codes are final and are to followed wherever contradictions observed above.

Signature of Architect-					                       Signature of Competent 					        	 Technical Authority of const. agency

09/12 SQ

CERTIFICATE – I

(This certificate is invariably be obtained from construction agency and submitted alongwith preliminary estimate)

Sub:	Estimate   for construction   of  _______________________________ at  KV __________________

This is to certify that estimate amounting to Rs. _____________________ submitted by our office for the above cited work is a consolidated estimate covering   the following provisions apart from construction of buildings as per scope including internal services :-

- Development of site i.e. internal roads/paths/retaining wall ( if required ), external water supply viz sump, tanks on building, pumps(submersible/booster), area drainage, external sewer arrangement viz. septic tank, soak pits etc.

- Bulk services (civil & elec.)

- Electric service connection including system strengthening. ( if required ) & charges payable to local Elec. Board, if any.

- Drinking water including connection and charges payable to local authorities ( if any) and tube-well ( if required )

- All provisions are made after ascertaining demand for proposed work and availability from various sources in the campus.

- Other provisions as per norms and site conditions,(  if any )

It is further certified that no demolition of existing structures, removal of electric lines, trees etc.  is required.

Further a set of line plan and location plan (duly marked in master plan) of the proposed construction are enclosed with estimate.  Being ‘Deposit Work’ necessary co-ordination is being made by this department with local authorities and ensure approval of drawings before and after execution of work.  However, Principal, KV will extend his help in this regard.

It is further certified that on completion, these structures can be put in use with commissioning of all services viz. Drinking water, electricity, sewage disposal etc. without any difficulty.

Signature of competent Technical Authority

of Construction Agency

09/12 ACR SQ

CERTIFICATE – II

(This certificate is invariably be furnished by Principal alongwith estimate)

Sub :  Estimate amounting to Rs. __________ framed by  _____________(Name             of construction agency ) for construction of ___________________________at KV, _________________________.

This is to certify that the above construction work has been planned on the overall land measuring _______ acres already transferred to this KV on lease / permanent grant basis . Further the piece of land is clear and free from obstructions, encroachments, trees, elec. Lines, litigations, court cases, and other physical/ infrastructural facilities etc.  already created by KV/ KVS. No demolition of existing facilities / structures is involved.

The proposed work and construction agency have been approved in VMC meeting held on __________. The location of proposed construction work has been decided by a team of officials of VMC (Chairman or his authorized representative), Construction agency, and the undersigned.

Signature of Principal

09/12 ACR SQ

CERTIFICATE –III

( To be obtained from competent authority of Sponsors )

GRANT OF APPROVAL FOR CONSTRUCTION

Principal, Kendriya  Vidyalaya ______________approached this office for grant of approval/ permission  to undertake construction of _______________

on the basis of  drawings developed and estimate framed by ______________

on the land measuring ________ acres allotted on  lease / permanent grant to this KV by _____________. As per allotment conditions prior permission / approval is to be obtained from competent authority.

The undersigned has no objection in taking up this work on the aforesaid land and approval / permission is hereby granted in this regard.

SIGNATURE OF COMPETENT AUTHORITY

WITH DATE & SEAL

Note:     For Defence secotor KVs  -  DEO  ( Compulsory ) and  also  Chairman , VMC ( or any other  authorized Officer )

For Railway Sector KVs - DRM and/or, GM (to be confirmed from sponsors) ,and also Chairman , VMC ( or any other  authorized officer )

For State Govt. Sector - DM/ Collector (or any other authorized officer)

For KVs not covered above - may be confirmed from Sponsors.

09/12 ACR SQ